## SLA Dashboard
EP01 SLA EXECUTIVE DASHBOARD
อัปเดตอัตโนมัติจากชีต Action Items & SLA
Total Actions =COUNTA('Action Items & SLA'!B2:B18) |  | Completed =COUNTIF('Action Items & SLA'!J2:J18,"Completed") |  | On Track =COUNTIF('Action Items & SLA'!J2:J18,"On Track") |  | At Risk =COUNTIF('Action Items & SLA'!J2:J18,"At Risk") |  | Overdue + Escalated =COUNTIF('Action Items & SLA'!J2:J18,"Overdue")+COUNTIF('Action Items & SLA'!J2:J18,"Escalated")
SLA Status | Count |  | Priority | Total | Open |  | Executive Indicator | Value
Completed |  |  | P1 |  |  |  | SLA Compliance %
On Track |  |  | P2 |  |  |  | Open P1
Pending |  |  | P3 |  |  |  | Next Due
At Risk |  |  | P4 |  |  |  | Overall SLA Health
Overdue
Escalated
Next Actions Requiring Attention
Priority | Action Item | Owner | SLA Due | Escalation | SLA Status

## SLA Formula Summary
SLA STATUS FORMULA SUMMARY
SLA Status | Count | % of Total | Definition | Executive Action | Color
Completed |  |  | งานเสร็จแล้ว | ไม่ต้องดำเนินการเพิ่มเติม | Green
On Track |  |  | ยังไม่ครบ SLA และเหลือเวลามากกว่า 25% | ติดตามตามแผน | Green
Pending |  |  | รอเริ่มงาน แต่ยังไม่เกิน SLA | Owner ยืนยันวันเริ่ม | Yellow
At Risk |  |  | เหลือเวลาไม่เกิน 25% ก่อนครบ SLA | เร่ง Owner และ Producer | Orange
Overdue |  |  | เกินเวลาครบ SLA แต่ยังไม่ถึงวัน Escalation | แก้ไขทันทีและแจ้ง Producer | Red
Escalated |  |  | เกินวันและเวลา Escalation | แจ้ง Executive Producer | Dark Red
Total Actions |  |  | สูตร SLA Status รายงาน
SLA Compliant |  |  | Completed overrides all statuses.
SLA Non-Compliant |  |  | Escalated: NOW() > Escalation Date/Time
SLA Compliance % |  |  | Overdue: NOW() > SLA Due Date/Time
Overall SLA Health |  |  | At Risk: อยู่ใน 20% สุดท้ายของ SLA
Next SLA Due |  |  | Pending: Work Status = Pending
Next Escalation |  |  | On Track: ยังไม่เข้าเงื่อนไขข้างต้น
Owner KPI Summary
Owner | Total | Open | At Risk | Overdue | Escalated | SLA Compliance %
Canon Director
Lead Writer
Art Director
Prompt Lead
Animation Lead
Producer
Art Team
Art QA
Canon Team
Editor Lead
Audio Lead
Marketing Lead
QC Lead
Executive Producer

## Executive QC Summary
EP01 Executive QC Summary
Episode | EP01 | Canon Health | MASTER CANON
ชื่อ | นักสืบกับความกล้าที่อยู่ปลายเชือก | CCI | 96
Runtime Target | 8:20 | Risk | LOW
Scenes | 11
Frames | 39
Production Status | UNLOCKED
หมวด | คะแนน | Department | Status
Timeline | 19 | Writing | Ready
Character | 20 | Storyboard | Ready
Location | 19 | Prompt Team | Ready
Mystery | 19 | Art Team | Ready
Arc Progression | 19 | Animation | Ready
CCI Total |  | Editing | Ready
|  | QC | Ready

## Canon QC Checklist
Category | Check Item | Status | Owner | Note
Story | Route อายุ 15 ปีตลอดตอน | PASS
Story | ไม่มีการเปิดเผยโรงเรียน Shared Memory หรือห้องแล็บ | PASS
Character | หมวก เป้ และเชือกของ Route ต่อเนื่อง | PASS
Character | Rabbit B มีผ้าพันคอเขียวหม่นและแผลหูขวา | PASS
Location | ประตูรั้วอยู่หลังป้อมยาม | PASS
Knowledge | Route ยังไม่รู้ชื่อ Rabbit B | PASS
Clue | เบาะแสทั้ง 7 จุดปรากฏครบ | PASS
Audio | BGM ไม่กลบบทพูด | PASS
Editing | ลำดับช็อต F1-F39 ครบ | PASS
Delivery | ความยาวรวมใกล้เป้า 8:20 | PASS

## Action Items & SLA
Priority | Action Item | Owner | Start Date/Time | SLA (Hours) | SLA Due Date/Time | Operational Due Date | Escalation Date/Time | Work Status | SLA Status | Notes
P1 | Canon Package Approval | Canon Director | 2026-09-29 18:30 | 24 |  |  |  | Pending
P1 | Script & Shot Breakdown Lock | Lead Writer | 2026-09-29 18:30 | 24 |  |  |  | Pending
P1 | Character Canon Approval | Art Director | 2026-09-30 18:30 | 48 |  |  |  | Pending
P1 | Image Prompt Approval | Prompt Lead | 2026-09-30 18:30 | 48 |  |  |  | Pending
P1 | Motion Prompt Approval | Animation Lead | 2026-09-30 18:30 | 72 |  |  |  | Pending
P2 | Asset Tracking Sheet | Producer | 2026-10-01 18:30 | 24 |  |  |  | Not Started
P2 | Key Asset Generation | Art Team | 2026-10-02 18:30 | 48 |  |  |  | Not Started
P2 | Character Consistency Review | Art QA | 2026-10-04 18:30 | 24 |  |  |  | Not Started
P2 | Canon Consistency Review | Canon Team | 2026-10-04 18:30 | 24 |  |  |  | Not Started
P3 | Subtitle Master | Editor Lead | 2026-10-06 18:30 | 24 |  |  |  | Not Started
P3 | Audio Cue Sheet | Audio Lead | 2026-10-06 18:30 | 24 |  |  |  | Not Started
P3 | Music Cue Sheet | Audio Lead | 2026-10-06 18:30 | 24 |  |  |  | Not Started
P3 | YouTube Metadata | Marketing Lead | 2026-10-07 18:30 | 24 |  |  |  | Not Started
P4 | Audio Mix Final Review | Audio Lead | 2026-10-09 18:30 | 24 |  |  |  | Not Started
P4 | Canon Final Audit | QC Lead | 2026-10-09 18:30 | 24 |  |  |  | Not Started
P4 | Final Render Approval | Editor Lead | 2026-10-10 18:30 | 12 |  |  |  | Not Started
P4 | Executive Release Approval | Executive Producer | 2026-10-10 18:30 | 12 |  |  |  | Not Started

## RACI Matrix
Activity | Executive Producer | Producer | Canon Director | Lead Writer | Art Director | Prompt Lead | Animation Lead | Editor Lead | Audio Lead | QC Lead | Marketing Lead
Canon Package Approval | A | I | R | C | [5 empty] | C
Script & Shot Lock |  | A | C | R |  |  | I | C
Character Canon Approval |  | A | C | C | R |  |  |  |  | I
Image Prompt Review |  | A | C | C | C | R
Motion Prompt Review |  | A | I |  |  | C | R | C
Asset Production |  | A |  |  | R | R | C |  |  | C
Animation Production |  | A |  |  | C |  | R | C |  | C
Editing Master |  | A |  |  |  |  | C | R | C | C
Audio Mix |  | A | [5 empty] | C | R | C
Canon Final Audit |  | I | A | C |  |  |  | C |  | R
YouTube Metadata |  | A |  | C |  |  |  | I |  |  | R
Release Approval | A | R | C |  |  |  |  | C |  | C | I
Legend
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed